## Sprint - 1
Sprint1-Sign Up & My Profile
SL.NO |  | Task | Assignee | Esti Hours | Act Hours | Start Date | End date | Act End Date | Status | Status | Descrption
1 | Login&Sign Up | Login & Signup Screens development | Dilip | 15 hours | 6 hours | 2018-03-08 | 2018-03-15 |  | Completed
2 |  | Login & Signup Code development | Srini/Parthiya | 10 hours |  | 2018-03-08 | 2018-03-17 |  | Completed
3 |  | Intigration | Srini/Parthiya | 5 hours |  | 2018-03-16 | 2018-03-17 |  | Completed
4 |  | Code review | Shoban | 5 hours |  | 2018-03-17 | 2018-03-17 |  | Completed
5 |  | Testing | Viswa | 10 hours |  | 2018-03-17 | 2018-03-17 |  | Working In Progress
6 |  | BRD Changes | Sadik | [5 empty] | ONGOING
7
8 | MY Profile | Add NewBusiness UI Development | Dilip | 12 Hours |  | 2018-03-16 | 2018-03-17 |  | Completed
9 |  | Add My new Business Java Development | Srini/Parthiya | 5 hours |  | 2018-03-16 | 2018-03-17 |  | Completed
10 |  | Intigration | Srini/Parthiya | 5 Hours |  | 2018-03-17 | 2018-03-17 |  | Completed
11 |  | Code Review | Shoban | 5 hours |  | 2018-03-17 | 2018-03-17 |  | Completed
12 |  | Testing | Viswa | 10 hours |  | 2018-03-17 | 2018-03-17 |  | WIP
13
14 |  | Edit My Information UI Development | Dilip | 12 Hours |  | 2018-03-18 | 2018-03-18 |  | Completed
15 |  | Edit My Information Java Development | Srini/Parthiya | 5 hours |  | 2018-03-18 | 2018-03-18 |  | Completed
16 |  | Intigration | Srini/Parthiya | 5 Hours |  | 2018-03-18 | 2018-03-18 |  | Completed
17 |  | Code Review | Shoban | 5 hours |  | 2018-03-18 | 2018-03-18 |  | Completed
18 |  | Testing | Viswa | 10 hours |  | 2018-03-18 | 2018-03-18 |  | WIP
19
20 | My Business Plan | My Rewards UI screens | Dilip | 15 Hours |  | 2018-03-20 | 2018-03-22 | 2018-03-28 | Done
21 |  | My Rewards Java Development | Parthiya | 15 hours |  | 2018-03-20 | 2018-03-24 | 2018-03-28 | done
22 |  | Intigration | dilip/Parthiya | 5 Hours |  | 2018-03-20 | 2018-03-24 | 2018-03-29 | done |  | Thursday 8AM
23 |  | Code review | Shoban | 5 hours |  | 2018-03-24 | 2018-03-24 |  | Need to Start
24 |  | Testing | Viswa | 10 hours |  | 2018-03-24 | 2018-03-24 |  | Need to Start
25 |  | BRD Changes | Sadik | 10hours |  |  |  | 2018-03-26
26 |  | My product Discounts Ui Development | Dilip | 15 Hours |  | 2018-03-24 | 2018-03-24 | 2018-03-31 | Completed
27 |  | My product Discounts Java Development | Parthiya | 15 Hours |  | 2018-03-24 | 2018-03-24 | 2018-03-31 | Completed
28 |  | Intigration | Dilip/Parthiya | 5 hours |  | 2018-03-24 | 2018-03-24 | 2018-03-31 | Completed
29 |  | Code review | Shoban | 5 hours |  | 2018-03-24 | 2018-03-24 |  | Completed
30 |  | Tesing | Viswa | 10 hours |  | 2018-03-24 | 2018-03-24 |  | Need to Start
31
32 |  | My Invoice Ui Development | Dilip | 25Hours |  | 2018-03-24 | 2018-03-25 | 2018-04-01 | WIP |  | One Invoice
33 |  | My Invoice Java Development | Parthiya | 15 Hours |  | 2018-03-24 | 2018-03-25 | 2018-04-01 | WIP
34 |  | Intigration | Dilip/Parthiya | 5 Hours |  | 2018-03-25 | 2018-03-25 |  | WIP
35 |  | Code review | Shoban | 5 hours |  | 2018-03-25 | 2018-03-25 |  | WIP
36 |  | Tesing | Viswa | 10 hours |  | 2018-03-25 | 2018-03-25 |  | Need to Start
37 |  | Moving To Prod | shoban |  |  | 2018-03-25 | 2018-03-25 | 2018-04-01 | Need to Start |  | Demo 10PM

## Queries
Pending Task
SL.NO | Task | Sub Task | Des | Solution | Status
| Login Page-1 | Remember password
Forget Password
| Login Page-2 | Password stength |  | Standard
|  | Email validation |  | Standard
|  | lattitude and longitude |  | Standard
|  | Reg id |  | Basic validation

## GAPS
SL.NO | Date | GAP | Detail Desc | Solution | Tasks
1 | 24/02/2018 | Technology Stack Finialzation | JAVA, Spring, Hibernet, Angular JS, Ebeded database(H2, DERBY) | Latest Version
2 | 24/02/2019 | Registration Account Number Generation | Logic Disscusion--Based on Business Category, Number Size..? | Business Category and Sequence Number
3 | 24/02/2020 | Registration Address--current location | Logic Required--paid one..? Or open source | Based on Auto filled, Google Api, | Shoban will send links | Based on pincode it display city, district, state
4 | 24/02/2021 | Database Desgin | Script/ | Dynamic |  | Current location from map, lattitude and longitude
5 | 24/02/2022 | OTP Generation | API..? | If Open Source was not Available we will go with paid one | Shoban will send links | otp
6 | 24/02/2023 | Photos | Size..? | Later On will Fix
7 | 24/02/2024 | Format |  | Generic |  | Web space
8 | 25/02/2017 | Github, |  |  | viswa create account
9 | 25/02/2017 | sonarqube, | static quality code analysis | Team Use this Tool
Multiple business, with more number of shops

## FLOW
TASK | UI WORK | JAVA WORK
Task 1 | User Enter SMYdata.com
Login page will be displayed,
Login
New user sign Up
For Get Password
Remember My password
Task 2 | Login Page fields validation
All links should work
Task 3 | Click On Login | Call Login Controller and validate user & Response
| Navigate to home Page And Display Info | use spring security
Task 4 | New user Sign Up Link | New signup controller & validate Registration Fields
If validation is done, will generate otp and response to UI
| Navigate to Registration Page | Validates OTP and allow user to create account and navigate to Home
Enter all details and validate
OTP Prompt Page
Eneter OTP Validate
If Valid OTP GOTO Home Page
Task 3 fallows

## Dilip
Sl.No | Task | Pending Works | Descrption
1 | sign Up Page and addNew business and edit myInfo | Location | get latitude and longitude
|  | validations | input validations, password required length,email id , mobile ,pin code, reg id.
id proof attachment
|  | otp number | only numbers are allowed to enter in OTP input
Saturday
2 | forgot pswd and sign up | resend otp | how many times user allowed to ask for resend??
3 | Edit my Info | Business category cannot able to change
Business ID cannot able to change

## Parthiya
Sl.No | Task | Pending Works | Descrption | End date
1 | session management
2 | intigration issues

## Meeting
Sunday 10PM IST | Work Assignment | Timings
| Functional Discuss | 15 min
| Technical Discusion | 15 min
| Questions | 15 min
| Completion Of backlog Work | 15 min
Thursday Status 8AM IST | Quick Status Update | 15min
Saturday 10PM IST | Task Progress | Timings
| UI Disscussion Pending | 15 Min
| Technical discussion Pending | 15 Min
| Demo | 15 Min
| Questions | 15 Min
Date | Time | Agenda
3/25/2018--Sunday | 10PM IST | Login Demo & My Business Plan Discussion
3/29/2018--Thursday | 8AM IST | Quick Status Update
3/31/2018--Saturday | 10PM IST | Demo On My Business Plan, Pending Works
4/01/2018--Saturday | 10PM IST | Functional/ TechDiscussion On Invoice Asper GST

## Sprint - 2
Sprint 2- After Login
SL.NO |  | Task | Assignee | Esti Hours | Act Hours | Start Date | End date | Act End Date | Status | Descrption
1 | Invoice As Per GST | Invoice As Per GST--No--Customer Login--UI | Dilip | 10 Hours |  | 2018-04-02 |  |  | Need to Start
2 |  | Invoice As Per GST--N0--Customer Login--Java | Parthiya | 10 Hours |  |  |  |  | Need to Start
3 |  | Intigration | Dilip/Parthiya | 5 hours |  |  |  |  | Need to Start
4 |  | Code review | Shoban | 5 hours |  |  |  |  | Need to Start
5 |  | Testing | Viswa/Sathya | 10 hours |  |  |  |  | Need to Start
6 |  | BRD Changes | Sadik | [5 empty] | ONGOING
7
8 | Invoice As Per GST | Invoice As Per GST--YES--Customer Login | Dilip | 10 Hours |  |  |  |  | Need to Start
9 |  | Invoice As Per GST--YES--Customer Login | Parthiya | 10 Hours |  |  |  |  | Need to Start
10 |  | Intigration | Dilip/Parthiya | 5 hours |  |  |  |  | Need to Start
11 |  | Code Review | Shoban | 5 hours |  |  |  |  | Need to Start
12 |  | Testing | Viswa/Sathya | 10 hours |  |  | 2018-04-08 |  | Need to Start
13 |  | BRD Changes | Sadik | [5 empty] | ONGOING
14
15 | Payables | Payables--No----UI development | Dilip | 10 Hours |  | 2018-04-09 |  |  | Need to Start
16 |  | Payables--N0---Java | Parthiya | 10 Hours |  |  |  |  | Need to Start
17 |  | Intigration | Dilip/Parthiya | 5 hours |  |  |  |  | Need to Start
18 |  | Code review | Shoban | 5 hours |  |  |  |  | Need to Start
19 |  | Testing | Viswa/Sathya | 10 hours |  |  |  |  | Need to Start
20 |  | BRD Changes | Sadik | [5 empty] | ONGOING
21
22 | Payables | Payables--YES---UI Development | Dilip | 10 Hours |  |  |  |  | Need to Start
23 |  | Payables--YES--Java | Parthiya | 10 Hours |  |  |  |  | Need to Start
24 |  | Intigration | Dilip/Parthiya | 5 hours |  |  |  |  | Need to Start
25 |  | Code Review | Shoban | 5 hours |  |  |  |  | Need to Start
26 |  | Testing | Viswa/Sathya | 10 hours |  |  | 2018-04-15 |  | Need to Start
27 |  | BRD Changes | Sadik | [5 empty] | ONGOING
28
29
30 | Recivables | Receivable--No----UI development | Dilip | 10 Hours |  | 2018-04-16 |  |  | Need to Start
31 |  | Receivable--N0---Java | Parthiya | 10 Hours |  |  |  |  | Need to Start
32 |  | Intigration | Dilip/Parthiya | 5 hours |  |  |  |  | Need to Start
33 |  | Code review | Shoban | 5 hours |  |  |  |  | Need to Start
34 |  | Testing | Viswa/Sathya | 10 hours |  |  |  |  | Need to Start
35 |  | BRD Changes | Sadik | [5 empty] | ONGOING
36
37 | Recivables | Receivable--YES---UI Development | Dilip | 10 Hours |  |  |  |  | Need to Start
38 |  | Receivable--YES--Java | Parthiya | 10 Hours |  |  |  |  | Need to Start
39 |  | Intigration | Dilip/Parthiya | 5 hours |  |  |  |  | Need to Start
40 |  | Code Review | Shoban | 5 hours |  |  |  |  | Need to Start
41 |  | Testing | Viswa/Sathya | 10 hours |  |  |  |  | Need to Start
42 |  | BRD Changes | Sadik | [5 empty] | ONGOING
43
44 | Ticket Raise | Request----UI development | Dilip | 10 Hours |  |  |  |  | Need to Start
45 |  | Request---Java | Parthiya | 10 Hours |  |  |  |  | Need to Start
46 |  | Intigration | Dilip/Parthiya | 5 hours |  |  |  |  | Need to Start
47 |  | Code review | Shoban | 5 hours |  |  |  |  | Need to Start
48 |  | Testing | Viswa/Sathya | 10 hours |  |  |  |  | Need to Start
49 |  | BRD Changes | Sadik |  |  |  | 2018-04-22 |  | ONGOING
50
51 | Reports | Report--filters--UI development | Dilip | 10 Hours |  | 2018-04-23 |  |  | Need to Start
52 |  | Reports--filters--Java | Parthiya | 10 Hours |  |  |  |  | Need to Start
53 |  | Intigration | Dilip/Parthiya | 5 hours |  |  |  |  | Need to Start
54 |  | Code review | Shoban | 5 hours |  |  |  |  | Need to Start
55 |  | Testing | Viswa/Sathya | 10 hours |  |  |  |  | Need to Start
56 |  | BRD Changes | Sadik | [5 empty] | ONGOING
57
58 | Reports | Reports---UI Development | Dilip | 10 Hours |  |  |  |  | Need to Start
59 |  | Reports---Java | Parthiya | 10 Hours |  |  |  |  | Need to Start
60 |  | Intigration | Dilip/Parthiya | 5 hours |  |  |  |  | Need to Start
61 |  | Code Review | Shoban | 5 hours |  |  |  |  | Need to Start
62 |  | Testing | Viswa/Sathya | 10 hours |  |  |  |  | Need to Start
63 |  | BRD Changes | Sadik |  |  |  | 2018-04-29 |  | ONGOING
64
65 | Admin Login | Admin Login---UI Development | Dilip | 10 Hours |  | 2018-04-30 |  |  | Need to Start
66 |  | Admin Login--Java | Parthiya | 10 Hours |  |  |  |  | Need to Start
67 |  | Intigration | Dilip/Parthiya | 5 hours |  |  |  |  | Need to Start
68 |  | Code Review | Shoban | 5 hours |  |  |  |  | Need to Start
69 |  | Testing | Viswa/Sathya | 10 hours |  |  |  |  | Need to Start
70 |  | BRD Changes | Sadik | [5 empty] | ONGOING
71 | Admin Login | Admin Login After Login---UI Development | Dilip | 10 Hours |  |  |  |  | Need to Start
72 |  | Admin Login After Login--Java | Parthiya | 10 Hours |  |  |  |  | Need to Start
73 |  | Intigration | Dilip/Parthiya | 5 hours |  |  |  |  | Need to Start
74 |  | Code Review | Shoban | 5 hours |  |  |  |  | Need to Start
75 |  | Testing | Viswa/Sathya | 10 hours |  |  |  |  | Need to Start
76 |  | BRD Changes | Sadik |  |  |  | 2018-05-06 |  | ONGOING