## Sprint - 1
Sprint1-Sign Up & My Profile
SL.NO |  | Task | Assignee | Esti Hours | Act Hours | Start Date | End date | Act End Date | Status | Descrption
1 | Login&Sign Up | Login & Signup Screens development | Dilip | 15 hours | 6 hours | 2018-03-08 | 2018-03-15 |  | Completed
2 |  | Login & Signup Code development | Srini/Parthiya | 10 hours |  | 2018-03-08 | 2018-03-17 |  | Completed
3 |  | Intigration | Srini/Parthiya | 5 hours |  | 2018-03-16 | 2018-03-17 |  | Working In Progress
4 |  | Code review | Shoban | 5 hours |  | 2018-03-17 | 2018-03-17 |  | Working In Progress
5 |  | Testing | Viswa | 10 hours |  | 2018-03-17 | 2018-03-17 |  | Working In Progress
6 |  | BRD Changes | Sadik | [5 empty] | ONGOING
7
8 | MY Profile | Add NewBusiness UI Development | Dilip | 12 Hours |  | 2018-03-16 | 2018-03-17 |  | Completed
9 |  | Add My new Business Java Development | Srini/Parthiya | 5 hours |  | 2018-03-16 | 2018-03-17 |  | Working In Progress
10 |  | Intigration | Srini/Parthiya | 5 Hours |  | 2018-03-17 | 2018-03-17 |  | Working In Progress
11 |  | Code Review | Shoban | 5 hours |  | 2018-03-17 | 2018-03-17 |  | Working In Progress
12 |  | Testing | Viswa | 10 hours |  | 2018-03-17 | 2018-03-17 |  | Working In Progress
13
14 |  | Edit My Information UI Development | Dilip | 12 Hours |  | 2018-03-18 | 2018-03-18 |  | Need to Start
15 |  | Edit My Information Java Development | Srini/Parthiya | 5 hours |  | 2018-03-18 | 2018-03-18 |  | Need to Start
16 |  | Intigration | Srini/Parthiya | 5 Hours |  | 2018-03-18 | 2018-03-18 |  | Need to Start
17 |  | Code Review | Shoban | 5 hours |  | 2018-03-18 | 2018-03-18 |  | Need to Start
18 |  | Testing | Viswa | 10 hours |  | 2018-03-18 | 2018-03-18 |  | Need to Start
19 | [8 empty] | Need to Start
20 | My Business Plan | My Rewards UI screens | Dilip | 15 Hours |  | 2018-03-20 | 2018-03-22 |  | Need to Start
21 |  | My Rewards Java Development | Srini/Parthiya | 15 hours |  | 2018-03-20 | 2018-03-24 |  | Need to Start
22 |  | Intigration | Srini/Parthiya | 5 Hours |  | 2018-03-20 | 2018-03-24 |  | Need to Start
23 |  | Code review | Shoban | 5 hours |  | 2018-03-24 | 2018-03-24 |  | Need to Start
24 |  | Testing | Viswa | 10 hours |  | 2018-03-24 | 2018-03-24 |  | Need to Start
25
26 |  | My product Discounts Ui Development | Dilip | 15 Hours |  | 2018-03-24 | 2018-03-24 |  | Need to Start
27 |  | My product Discounts Java Development | Srini/Parthiya | 15 Hours |  | 2018-03-24 | 2018-03-24 |  | Need to Start
28 |  | Intigration | Srini/Parthiya | 5 hours |  | 2018-03-24 | 2018-03-24 |  | Need to Start
29 |  | Code review | Shoban | 5 hours |  | 2018-03-24 | 2018-03-24 |  | Need to Start
30 |  | Tesing | Viswa | 10 hours |  | 2018-03-24 | 2018-03-24 |  | Need to Start
31
32 |  | My Invoice Ui Development | Dilip | 25Hours |  | 2018-03-24 | 2018-03-25 |  | Need to Start
33 |  | My Invoice Java Development | Srini/Parthiya | 15 Hours |  | 2018-03-24 | 2018-03-25 |  | Need to Start
34 |  | Intigration | Srini/Parthiya | 5 Hours |  | 2018-03-25 | 2018-03-25 |  | Need to Start
35 |  | Code review | Shoban | 5 hours |  | 2018-03-25 | 2018-03-25 |  | Need to Start
36 |  | Tesing | Viswa | 10 hours |  | 2018-03-25 | 2018-03-25 |  | Need to Start
37 |  | Moving To Prod | shoban |  |  | 2018-03-25 | 2018-03-25 |  | Need to Start

## Queries
Pending Task
SL.NO | Task | Sub Task | Des | Solution | Status
| Login Page-1 | Remember password
Forget Password
| Login Page-2 | Password stength |  | Standard
|  | Email validation |  | Standard
|  | lattitude and longitude |  | Standard
|  | Reg id |  | Basic validation

## GAPS
SL.NO | Date | GAP | Detail Desc | Solution | Tasks
1 | 24/02/2018 | Technology Stack Finialzation | JAVA, Spring, Hibernet, Angular JS, Ebeded database(H2, DERBY) | Latest Version
2 | 24/02/2019 | Registration Account Number Generation | Logic Disscusion--Based on Business Category, Number Size..? | Business Category and Sequence Number
3 | 24/02/2020 | Registration Address--current location | Logic Required--paid one..? Or open source | Based on Auto filled, Google Api, | Shoban will send links | Based on pincode it display city, district, state
4 | 24/02/2021 | Database Desgin | Script/ | Dynamic |  | Current location from map, lattitude and longitude
5 | 24/02/2022 | OTP Generation | API..? | If Open Source was not Available we will go with paid one | Shoban will send links | otp
6 | 24/02/2023 | Photos | Size..? | Later On will Fix
7 | 24/02/2024 | Format |  | Generic |  | Web space
8 | 25/02/2017 | Github, |  |  | viswa create account
9 | 25/02/2017 | sonarqube, | static quality code analysis | Team Use this Tool
Multiple business, with more number of shops

## FLOW
TASK | UI WORK | JAVA WORK
Task 1 | User Enter SMYdata.com
Login page will be displayed,
Login
New user sign Up
For Get Password
Remember My password
Task 2 | Login Page fields validation
All links should work
Task 3 | Click On Login | Call Login Controller and validate user & Response
| Navigate to home Page And Display Info | use spring security
Task 4 | New user Sign Up Link | New signup controller & validate Registration Fields
If validation is done, will generate otp and response to UI
| Navigate to Registration Page | Validates OTP and allow user to create account and navigate to Home
Enter all details and validate
OTP Prompt Page
Eneter OTP Validate
If Valid OTP GOTO Home Page
Task 3 fallows